## Phase 1 – HLD
PHASE 1 – HIGH LEVEL DESIGN (HLD)
# | Component | Type | Responsibility | Inputs | Outputs | Tech Stack | Notes / Dependencies | Deployed On | Phase | Status
1 | React UI | Frontend | Web app used by QA Engineer to upload project documents (PDFs, Swagger, .env files, URLs), trigger ingestion, and poll for status updates. | User actions; file uploads; polling calls | Uploads sent to FastAPI; polls Project ID for status | React.js, Axios, TailwindCSS | Communicates with FastAPI via REST. Hosts upload form and status indicator. | Client Browser | Phase 1 | Planned
2 | FastAPI Backend | Backend / Orchestrator | Central hub that receives REST requests from React UI, performs synchronous validation (liveness + credential check), initialises project record in DB, and triggers Temporal workflow. | REST calls from React UI; uploaded files | Project ID returned to UI; Project record in PostgreSQL; Temporal workflow triggered | Python, FastAPI, SQLAlchemy, Prance (Swagger parser) | Deployed on Azure Ubuntu VM. Manages sync validation phase and async handoff. | Azure Ubuntu VM | Phase 1 | Planned
3 | Temporal Orchestrator | Workflow Engine | Durable execution engine that runs the async ingestion pipeline. Retries failed steps, maintains workflow state, and sequences all ingestion activities. | Trigger signal from FastAPI with project metadata | Coordinated execution of ingestion steps; activity results | Temporal (self-hosted or Temporal Cloud), Python SDK | Handles all async steps after sync validation. Ensures fault-tolerant execution. | Azure Ubuntu VM | Phase 1 | Planned
4 | Azure Blob Storage | Cloud Storage | Stores raw uploaded files (PDFs, Swagger specs) offloaded from the FastAPI backend during ingestion. Acts as durable file store for large binary content. | Raw PDFs and Swagger files from Temporal activity | Stored file references (URLs/paths) for downstream steps | Azure Blob Storage SDK (Python) | Files are routed here before text extraction. Offloads heavy file storage from VM disk. | Azure Managed Service | Phase 1 | Planned
5 | Azure PostgreSQL | Relational Database | Stores all structured project metadata: project records, ingestion status, extracted text snippets, flattened Swagger endpoints. Single source of truth for project state. | Project records from FastAPI; extracted text from Temporal; API endpoints | Queryable project and document data | PostgreSQL, SQLAlchemy ORM, Alembic (migrations) | Stores status field updated throughout pipeline. Phase 2 reads Scenarios/Tasks from here. | Azure Managed Service | Phase 1 | Planned
6 | PyMuPDF (Text Extraction) | Processing Library | Extracts raw text content from uploaded PDF documents. Runs inside a Temporal activity on the FastAPI backend VM. | PDF file (from Blob Storage reference) | Extracted raw text string per PDF | PyMuPDF (fitz), Python | Text extraction activity invoked by Temporal. Output saved to PostgreSQL. | Azure Ubuntu VM | Phase 1 | Planned
7 | Prance (Swagger Parser) | Processing Library | Parses and resolves Swagger / OpenAPI specification files. Flattens all API endpoint definitions for storage and downstream vector embedding. | Swagger/OpenAPI YAML or JSON file | Flattened list of API endpoint objects (method, path, description, params) | Prance, Python | Runs as a Temporal activity. Output stored in PostgreSQL as structured endpoint rows. | Azure Ubuntu VM | Phase 1 | Planned
8 | Sliding Window Chunker | Processing Utility | Splits extracted text documents into overlapping chunks suitable for embedding. Uses sliding window strategy to preserve context at chunk boundaries. | Extracted text from PostgreSQL | List of text chunks with metadata (doc_id, chunk_index, offset) | Python (custom utility / LangChain text splitter) | Chunk size and overlap configurable. Feeds directly into embedding generation. | Azure Ubuntu VM | Phase 1 | Planned
9 | Local Embedding Model (all-MiniLM-L6-v2) | AI / ML Model | Generates dense vector embeddings for each text chunk. Runs locally on the Azure VM to avoid external API costs and latency. | Text chunks from Sliding Window Chunker | 384-dimensional vector per chunk | sentence-transformers, all-MiniLM-L6-v2, Python | Model loaded once and cached. Self-loop on FastAPI Backend indicates local execution. | Azure Ubuntu VM | Phase 1 | Planned
10 | Qdrant Vector DB | Vector Store | Stores and indexes all vector embeddings generated from ingested documents. Supports SHA-256 based deduplication on upsert. Queried by Phase 2 agents via MCP. | Vector embeddings + chunk metadata from embedding model | Top-K similar chunks on query; deduplication on upsert | Qdrant (Docker container on Azure VM) | SHA-256 hash of chunk text used as point ID for deduplication. Read-only for Phase 2. | Azure Ubuntu VM (Docker) | Phase 1 | Planned

## Phase 1 – LLD
PHASE 1 – LOW LEVEL DESIGN (LLD)
# | Module | Sub-Component / Function | Description | Input | Output / Return | DB Tables Affected | API Endpoint | Error Handling | Notes
1 | React UI | UploadProjectForm | Form component allowing QA Engineer to upload PDFs, Swagger file, .env file, and enter a target URL. Submits multipart/form-data POST to /api/v1/projects. | User file inputs, URL text field | POST /api/v1/projects called; receives Project ID; begins polling | Projects (WRITE via backend) | POST /api/v1/projects | Show validation error if no files attached; show network error toast on 5xx | Disables submit button while upload in progress. Switches to polling view on success.
2 | React UI | StatusPoller | After receiving Project ID, polls GET /api/v1/projects/{id} every 3 seconds. Updates status indicator chip. Stops polling when status = 'Ingestion Complete' or error. | Project ID from upload response | Live status displayed to user | Projects (READ) | GET /api/v1/projects/{project_id} | Show error state if polling returns 404 or 500; exponential backoff after 5 failures | Status values: Pending → Processing → Ingestion Complete / Failed
3 | FastAPI | POST /api/v1/projects | Receives multipart upload. Validates files present and credentials reachable (liveness ping). Initialises Project record in DB with status='Pending'. Triggers Temporal workflow. Returns Project ID immediately (202). | Multipart: PDFs, Swagger, .env, URL string | project_id: UUID, status: 'Pending' | Projects (WRITE) | POST /api/v1/projects | 400 if required files missing; 503 if liveness ping fails; 500 on DB write error | Uses FastAPI BackgroundTasks to trigger Temporal non-blocking. Returns 202 Accepted.
4 | FastAPI | Liveness Ping & Credential Check | Before initialising project record, FastAPI pings itself (health check) and validates any credentials provided in .env (e.g. API keys, DB connection). Synchronous gate. | .env file content parsed as key-value pairs | Pass / Fail signal | None | Internal (called within POST /api/v1/projects handler) | Return 503 with message if liveness fails; 401 if credentials invalid | Keeps synchronous phase fast. Only basic reachability checked, not deep validation.
5 | FastAPI | GET /api/v1/projects/{id} | Returns current project metadata and ingestion status. Called repeatedly by React UI poller. | project_id: UUID (path param) | Project object: id, status, created_at, updated_at | Projects (READ) | GET /api/v1/projects/{project_id} | 404 if project not found; 500 if DB unreachable | Status field updated by Temporal activities as pipeline progresses.
6 | PostgreSQL | Table: Projects | Stores top-level project records created on upload. Tracks overall ingestion status and links to uploaded files. | FastAPI insert on project creation; Temporal status updates | Project rows queryable by React UI | Projects | GET, POST /api/v1/projects | ProjectID PK unique constraint; Status enum constraint | ProjectID: UUID PK ¦ ProjectName: VARCHAR ¦ Status: VARCHAR ¦ CreatedAt: TIMESTAMP ¦ UpdatedAt: TIMESTAMP
7 | PostgreSQL | Table: Documents | Stores extracted text and file references for each uploaded document linked to a project. | Temporal activity writes after extraction | Document rows with raw text and blob path | Documents | Internal (Temporal writes directly via SQLAlchemy) | FK constraint on ProjectID → Projects; handle duplicate file uploads gracefully | DocID: UUID PK ¦ ProjectID: UUID FK ¦ DocType: VARCHAR ¦ BlobPath: VARCHAR ¦ ExtractedText: TEXT ¦ CreatedAt: TIMESTAMP
8 | PostgreSQL | Table: APIEndpoints | Stores flattened Swagger endpoint objects parsed by Prance. Each row = one API endpoint from the spec. | Temporal Prance-parser activity | Endpoint rows queryable for Phase 2 agent context | APIEndpoints | Internal (Temporal writes) | FK on ProjectID; ignore duplicate path+method combos | EndpointID: UUID PK ¦ ProjectID: UUID FK ¦ Method: VARCHAR ¦ Path: VARCHAR ¦ Description: TEXT ¦ Parameters: JSONB
9 | Temporal Orchestrator | Ingestion Workflow Definition | Defines the ordered sequence of ingestion activities: BlobUpload → TextExtraction → SwaggerParse → Chunking → Embedding → VectorUpsert → StatusUpdate. Handles retries and timeouts per activity. | Trigger payload: project_id, file paths, doc types | Workflow result: success or failure with error details | Projects (status updates via activities) | N/A (internal Temporal workflow) | Per-activity retry policy (3 attempts, exponential backoff); workflow timeout 30 min | Each activity is idempotent. Workflow can be re-run safely on partial failure.
10 | Temporal Orchestrator | BlobUploadActivity | Uploads raw PDF and Swagger files from local FastAPI temp storage to Azure Blob Storage. Returns blob URLs/paths for downstream activities. | Local file paths, Azure Blob container config | Blob path strings per file | None | N/A (internal Temporal activity) | Retry 3x on transient Azure SDK errors; fail workflow on auth error | Uses Azure SDK DefaultAzureCredential. Container created if not exists.
11 | Temporal Orchestrator | TextExtractionActivity | Calls PyMuPDF (fitz) to extract text from each PDF blob. Returns extracted text per document. Saves result to Documents table. | Blob path of PDF file | Extracted text string; writes to Documents table | Documents (WRITE) | N/A (internal Temporal activity) | Skip and log if PDF is image-only (no extractable text); retry 2x on IO error | Runs on FastAPI VM. PyMuPDF reads from local temp copy of blob.
12 | Temporal Orchestrator | SwaggerParseActivity | Loads Swagger/OpenAPI blob, resolves all $ref references via Prance, and flattens into endpoint objects. Stores each endpoint row in APIEndpoints table. | Blob path of Swagger file | List of endpoint objects; writes to APIEndpoints table | APIEndpoints (WRITE) | N/A (internal Temporal activity) | Fail activity if Swagger file is malformed; log parse warnings | Supports YAML and JSON OpenAPI formats. Uses prance.ResolvingParser.
13 | Temporal Orchestrator | ChunkingActivity | Reads extracted text from Documents table for a project. Applies sliding window chunking (configurable chunk_size and overlap). Returns list of chunk objects with metadata. | Extracted text from Documents table; chunk_size, overlap env vars | List of chunk dicts: {text, doc_id, chunk_index, project_id} | None (in-memory, passed to next activity) | N/A (internal Temporal activity) | Handle empty text gracefully (skip doc); log chunk count per document | Default: chunk_size=512 tokens, overlap=50 tokens. Configurable via ENV.
14 | Temporal Orchestrator | EmbeddingActivity | Loads all-MiniLM-L6-v2 model (cached on VM). Generates 384-dim embeddings for each text chunk. Returns list of vectors paired with chunk metadata. | List of chunk dicts from ChunkingActivity | List of {vector: [float], payload: {doc_id, chunk_index, text}} | None | N/A (internal Temporal activity) | Retry 2x on model inference error; batch chunks in groups of 64 for memory efficiency | Model loaded once per worker process and cached. No external API calls.
15 | Temporal Orchestrator | VectorUpsertActivity | Upserts all vector embeddings into Qdrant. Uses SHA-256 hash of chunk text as point ID for deduplication. Skips existing identical chunks. | List of {vector, payload} from EmbeddingActivity; Qdrant collection name | Upsert count; skipped (duplicate) count | None (Qdrant external) | N/A (internal Temporal activity) | Retry 3x on Qdrant connection error; log skipped duplicates | Collection created if not exists. SHA-256 ensures same content never duplicated across runs.
16 | Temporal Orchestrator | StatusUpdateActivity | Final activity in workflow. Updates Project record status to 'Ingestion Complete' in PostgreSQL. Timestamps UpdatedAt. | project_id; final status string | Updated Project record | Projects (UPDATE) | N/A (internal Temporal activity) | Retry 3x on DB write failure; if all fail, log critical and leave status as Processing | Called as last step regardless of partial failures in optional activities.
17 | Azure Blob Storage | File Routing | Raw PDFs and Swagger files are uploaded to a dedicated Azure Blob container per project. Provides durable storage accessible to all VM-based activities. | Binary file content from FastAPI temp upload | Blob URL / path string | None | N/A (Azure SDK calls) | Handle 403 auth errors with clear message; handle quota exceeded errors | Container naming: project-{project_id}. Files named by original filename + timestamp.
18 | Qdrant Vector DB | Collection & Upsert | Maintains a single Qdrant collection for Phase 1 ingested embeddings. Each point: id=SHA256(chunk_text), vector=384-dim float array, payload={project_id, doc_id, doc_type, text, chunk_index}. | Vector + payload from EmbeddingActivity | Upsert acknowledgement; search results (Top-K) on query | None (Qdrant internal) | Exposed via fetch_vector_context MCP tool in Phase 2 | Handle collection not found with auto-create; handle dimension mismatch as fatal error | Collection: 'phase1_docs'. Distance metric: Cosine. Vectors dimension: 384.

## Phase 1 – Sprint Planning
PHASE 1 – SPRINT PLANNING & USER STORIES (Start: 1 April 2026)
# | USN Items | Dev Effort (Days) | UT Effort (Days) | Total Effort (Days) | Epic | User Story | Feature(s) to Build | Acceptance Criteria | Assigned To | Sprint / Week | Est. Start | Est. End | Effort (Days) | Priority | Status
1 | Project Upload & Ingestion API | 2 | 0.5 | 2.5 | Document Ingestion | As a QA Engineer, I want to upload project documents (PDFs, Swagger, .env, URL) so that the system can ingest them and make them searchable. | 1. POST /api/v1/projects endpoint 2. Multipart file upload handling 3. Input validation (required files check) 4. Project record INSERT (status=Pending) 5. Return project_id + 202 Accepted | 1. Upload with all file types succeeds 2. project_id returned immediately 3. Missing files return 400 4. DB record created with status=Pending 5. Endpoint documented in /docs | Dev 1 + Dev 2 | Week 1 | 01-Apr-2026 | 07-Apr-2026 | 5 | P1 - Critical | Not Started
2 | Synchronous Liveness & Credential Check | 1 | 0.25 | 1.25 | Document Ingestion | As a system, I want to validate credentials and liveness synchronously before starting ingestion so that failures are caught early and reported clearly. | 1. Liveness ping (self health check) 2. .env credential parsing and basic validation 3. Return 503 on liveness fail 4. Return 401 on credential fail 5. Gate: only proceed if all checks pass | 1. Valid credentials → proceed to ingestion 2. Invalid creds → 401 with clear message 3. Liveness fail → 503 4. Check completes within 2 seconds 5. No project record created on failure | Dev 2 | Week 1 | 01-Apr-2026 | 03-Apr-2026 | 2 | P1 - Critical | Not Started
3 | Temporal Workflow – Ingestion Pipeline | 3 | 0.5 | 3.5 | Document Ingestion | As a system, I want the ingestion pipeline to run as a Temporal durable workflow so that each step is fault-tolerant, retriable, and observable. | 1. Temporal workflow definition 2. Activity sequence: BlobUpload → TextExtract → SwaggerParse → Chunk → Embed → VectorUpsert → StatusUpdate 3. Per-activity retry policies 4. Workflow timeout (30 min) 5. Workflow trigger from FastAPI background task | 1. Workflow starts within 1 sec of project creation 2. Each activity retries 3x on transient error 3. Status updated at each stage 4. Workflow observable in Temporal UI 5. Re-run on failure is idempotent | Dev 1 + Dev 2 | Week 1–2 | 01-Apr-2026 | 14-Apr-2026 | 8 | P1 - Critical | Not Started
4 | Azure Blob Storage – File Upload Activity | 1 | 0.25 | 1.25 | Document Ingestion | As a system, I want raw uploaded files to be stored in Azure Blob Storage so that large binary files are durably stored and accessible to downstream activities. | 1. BlobUploadActivity implementation 2. Azure SDK integration (DefaultAzureCredential) 3. Container per project naming convention 4. Return blob paths to workflow state 5. Handle container auto-creation | 1. Files uploaded to correct container 2. Blob paths returned to next activity 3. Auth error returns clear failure message 4. Activity retries on transient network error 5. Container named project-{project_id} | Dev 2 | Week 1 | 01-Apr-2026 | 04-Apr-2026 | 3 | P1 - Critical | Not Started
5 | PDF Text Extraction (PyMuPDF) | 1.5 | 0.5 | 2 | Document Ingestion | As a system, I want to extract raw text from uploaded PDF documents using PyMuPDF so that document content is available for chunking and embedding. | 1. TextExtractionActivity using PyMuPDF (fitz) 2. Read PDF from blob path 3. Extract text page by page 4. Save extracted text to Documents table 5. Handle image-only PDFs gracefully | 1. Text extracted successfully from text PDFs 2. Documents table row created with text 3. Image-only PDFs skipped with log entry 4. Activity retries 2x on IO error 5. Empty text handled without crash | Dev 2 | Week 1 | 03-Apr-2026 | 07-Apr-2026 | 3 | P1 - Critical | Not Started
6 | Swagger Spec Parsing (Prance) | 1.5 | 0.5 | 2 | Document Ingestion | As a system, I want Swagger/OpenAPI specs to be parsed and flattened into endpoint records so that API endpoints are individually stored and searchable. | 1. SwaggerParseActivity using Prance 2. Support YAML and JSON formats 3. Resolve all $ref references 4. Flatten endpoints: method, path, description, params 5. Insert rows to APIEndpoints table | 1. Valid Swagger parsed without error 2. All endpoints stored as individual rows 3. YAML and JSON both supported 4. Malformed Swagger fails activity with clear log 5. Duplicate path+method ignored | Dev 2 | Week 2 | 08-Apr-2026 | 11-Apr-2026 | 3 | P2 - High | Not Started
7 | Document Chunking (Sliding Window) | 1 | 0.25 | 1.25 | Document Ingestion | As a system, I want extracted document text to be split into overlapping chunks so that context is preserved at boundaries and embedding quality is maximised. | 1. ChunkingActivity implementation 2. Sliding window logic (chunk_size, overlap) 3. Chunk metadata: doc_id, chunk_index, project_id 4. Configurable via CHUNK_SIZE_TOKENS and OVERLAP_TOKENS env vars 5. Handle empty text gracefully | 1. Text split into correctly sized chunks 2. Overlap applied at boundaries 3. Chunk count logged per document 4. Empty documents skipped without crash 5. Config values loaded from ENV | Dev 1 | Week 2 | 08-Apr-2026 | 10-Apr-2026 | 2 | P1 - Critical | Not Started
8 | Local Embedding Generation (all-MiniLM-L6-v2) | 2 | 0.5 | 2.5 | Document Ingestion | As a system, I want vector embeddings to be generated locally using all-MiniLM-L6-v2 so that chunks are vectorised without external API cost or latency. | 1. EmbeddingActivity using sentence-transformers 2. Model load and cache on VM (one-time) 3. Batch inference in groups of 64 4. Return 384-dim float vectors per chunk 5. Pair vectors with chunk metadata | 1. Embeddings generated for all chunks 2. Model cached and not reloaded per activity 3. Batch size configurable via ENV 4. Output dimension is 384 5. Inference error retried 2x | Dev 1 | Week 2 | 10-Apr-2026 | 14-Apr-2026 | 4 | P1 - Critical | Not Started
9 | Qdrant Vector Upsert (SHA-256 Dedup) | 1.5 | 0.5 | 2 | Vector Store | As a system, I want embeddings upserted into Qdrant with SHA-256 deduplication so that the same content is never stored twice across ingestion runs. | 1. VectorUpsertActivity using Qdrant Python client 2. SHA-256 hash of chunk text as point ID 3. Upsert with vector + payload 4. Collection auto-create if not exists 5. Log skipped duplicate count | 1. All new chunks upserted to Qdrant 2. Duplicate chunks skipped (not duplicated) 3. Collection 'phase1_docs' exists after activity 4. Point payload includes project_id, doc_type, text 5. Retry 3x on connection error | Dev 1 | Week 3 | 15-Apr-2026 | 18-Apr-2026 | 3 | P1 - Critical | Not Started
10 | PostgreSQL – Projects & Documents Tables | 1 | 0.25 | 1.25 | Database & API | As a developer, I want Projects and Documents PostgreSQL tables set up with defined schemas so that project and document data is persistently stored. | 1. Projects table migration (Alembic) 2. Documents table migration 3. APIEndpoints table migration 4. SQLAlchemy ORM models for all tables 5. FK constraints and indexes | 1. All tables created with correct columns 2. FK constraints enforced 3. Alembic migration runs cleanly 4. UUID PKs auto-generated 5. Indexes on ProjectID in child tables | Dev 1 | Week 1 | 01-Apr-2026 | 03-Apr-2026 | 2 | P1 - Critical | Not Started
11 | React UI – Upload Form & Status Polling | 2 | 0.25 | 2.25 | Frontend | As a QA Engineer, I want a simple upload form in the React app so that I can submit project documents and see the ingestion status in real time. | 1. UploadProjectForm React component 2. Multipart POST to /api/v1/projects 3. StatusPoller component (polls GET /api/v1/projects/{id} every 3s) 4. Status chip: Pending / Processing / Complete / Failed 5. Error toast on failure | 1. Form accepts PDF, Swagger, .env, URL 2. Submit triggers upload and shows spinner 3. Status chip updates automatically 4. 'Ingestion Complete' shown when done 5. Error displayed clearly on failure | Dev 3 | Week 2 | 08-Apr-2026 | 14-Apr-2026 | 4 | P2 - High | Not Started
12 | fetch_vector_context MCP Tool Endpoint | 1.5 | 0.5 | 2 | Vector Store | As the Phase 2 system, I want a fetch_vector_context MCP tool endpoint exposed by FastAPI so that Phase 2 LangGraph agents can query Phase 1 vector embeddings. | 1. FastMCP server setup on FastAPI 2. fetch_vector_context tool: accepts query_text, doc_type filter, top_k 3. Embed query with same local model 4. Qdrant search with filter 5. Return top-K chunk objects | 1. MCP tool callable from LangGraph 2. Supports doc_type filter (BRD, Swagger, etc.) 3. Returns top_k chunks with text + metadata 4. Empty result handled gracefully 5. Response time < 2s for typical query | Dev 1 + Dev 2 | Week 3 | 15-Apr-2026 | 18-Apr-2026 | 4 | P1 - Critical | Not Started
13 | Azure VM – Deployment & Environment Setup | 2 | 0.5 | 2.5 | Infrastructure | As a team, I want all Phase 1 services deployed and running on the Azure Ubuntu VM so that the full ingestion pipeline is operational in the target environment. | 1. Docker compose / systemd for FastAPI, Qdrant, Temporal 2. Environment variable configuration (.env) 3. PostgreSQL connection from FastAPI 4. Temporal worker registration 5. Basic smoke test post-deploy | 1. All services start without error on Azure VM 2. FastAPI reachable from React UI 3. Temporal UI accessible 4. Qdrant reachable from FastAPI 5. End-to-end ingestion smoke test passes | Dev 1 + Dev 3 | Week 4 | 22-Apr-2026 | 28-Apr-2026 | 4 | P2 - High | Not Started
14 | E2E Integration Testing – Phase 1 | 2 | 0.5 | 2.5 | Integration & Testing | As a team, we want an end-to-end integration test of the full Phase 1 ingestion flow so that we can confirm the pipeline works before Phase 2 begins. | 1. E2E test script: upload docs → poll status → verify Qdrant vectors inserted 2. Verify Documents table populated 3. Verify APIEndpoints table populated 4. Verify fetch_vector_context MCP returns results 5. Bug fixes from integration findings | 1. Full ingestion completes without errors 2. Qdrant collection has correct vector count 3. Documents and APIEndpoints tables populated 4. MCP tool returns relevant chunks 5. Demo-ready for mentor presentation | All Devs | Week 5 | 29-Apr-2026 | 05-May-2026 | 5 | P1 - Critical | Not Started
TOTALS | Phase 1 Total | 23 | 5.75 | 28.75 | [8 empty] | 52

## Summary Dashboard
PHASE 1 – PROJECT SUMMARY DASHBOARD
Total User Stories | Total Dev Effort (Days) | Total UT Effort (Days) | Total Effort (Days) | P1 Critical Items | P2 High Items | Sprint Weeks | Target Go-Live
14 | 23 | 5.75 | 28.75 | 9 | 4 | 5 | 05-May-2026
SPRINT TIMELINE
Sprint | Week | Start Date | End Date | Focus | Stories | Assigned | Status
Sprint 1 | Week 1 | 01-Apr-2026 | 07-Apr-2026 | Project Upload API + DB Setup + Blob Upload + Text Extraction | USN 1, 2, 4, 5, 10 | Dev 1, Dev 2 | Not Started
Sprint 2 | Week 2 | 08-Apr-2026 | 14-Apr-2026 | Temporal Workflow + Swagger Parse + Chunking + Embedding + React UI | USN 3, 6, 7, 8, 11 | Dev 1, Dev 2, Dev 3 | Not Started
Sprint 3 | Week 3 | 15-Apr-2026 | 21-Apr-2026 | Qdrant Upsert + MCP Tool Endpoint | USN 9, 12 | Dev 1, Dev 2 | Not Started
Sprint 4 | Week 4 | 22-Apr-2026 | 28-Apr-2026 | Azure VM Deployment + Environment Setup | USN 13 | Dev 1, Dev 3 | Not Started
Sprint 5 | Week 5 | 29-Apr-2026 | 05-May-2026 | E2E Integration Testing + Bug Fixes + Demo Prep | USN 14 | All Devs | Not Started
PHASE 1 COMPONENT OVERVIEW
Component | Type | Tech | Phase | Deployed On | Role in Pipeline
React UI | Frontend | React, TailwindCSS | Phase 1 | Browser | Upload form + status polling
FastAPI Backend | Orchestrator | Python, FastAPI, SQLAlchemy | Phase 1 | Azure Ubuntu VM | Sync validation + Temporal trigger + MCP host
Temporal Orchestrator | Workflow | Temporal, Python SDK | Phase 1 | Azure Ubuntu VM | Durable async ingestion pipeline
Azure Blob Storage | Storage | Azure SDK | Phase 1 | Azure Managed | Raw PDF/Swagger file store
Azure PostgreSQL | Database | PostgreSQL, Alembic | Phase 1 | Azure Managed | Project + Document + Endpoint metadata
PyMuPDF | Library | fitz, Python | Phase 1 | Azure Ubuntu VM | PDF text extraction
Prance | Library | Prance, Python | Phase 1 | Azure Ubuntu VM | Swagger $ref resolution + flattening
Sliding Window Chunker | Utility | Python / LangChain | Phase 1 | Azure Ubuntu VM | Text chunking with overlap
all-MiniLM-L6-v2 | ML Model | sentence-transformers | Phase 1 | Azure Ubuntu VM | Local 384-dim embedding generation
Qdrant Vector DB | Vector Store | Qdrant Docker | Phase 1 | Azure Ubuntu VM | SHA-256 dedup vector storage